## Sheet1
| Name: Daniel Cyril Obon | ID: C2650218
Ref | The Risk |  |  | Inherent Risk Assessment |  |  | Reducing The Risk [Planned controls shown in YELLOW] |  | Residual Risk Assessment |  |  | Overall Risk Score Key:
# | Risk Cause and Event | Risk Consequences | Risk Owner | Probability | Impact | Overall | Control Measures (In place and planned) | Date / In place | Probability | Impact | Overall | Score | Risk
1 | Desktop machines running a mixture of Operating Systems runs Windows seven SP2, Windows 11 and Ubuntu 18 Different OS get updates at different times and consistencies | • Increased security risk • Inefficiency caused in workplace • Compatibility issues between machines | Support Centre Company | 0.7 | 70 | 49 | A) Ensure all machines used should be of the same operating system | In place | 0.2 | 40 | 8 | 1-10 | Low Risk
[7 empty] | B) Hold a workshop in teaching employees on using the selected operating system | In place |  |  |  | 11-50 | Medium Risk
[7 empty] | C) Provide machines for those without selected operating system | In place |  |  |  | 51-100 | High Risk
[7 empty] | D) Demonstrate the advantages of having using the same OS for work to employees | In place
2 | Servers running Windows 2016 using Domain controller Later versions of Windows will be released making the current serve being used outdated | • Increased security risk • Not futureproof | Operating System | 1.0 | 90 | 90 | A) Check for any major updates frequently | In place | 0.5 | 90 | 45
[7 empty] | B) Hold a workshop in teaching employees on using the selected operating system | In place
[7 empty] | Update server when a major update is needed | When available
3 | Subnets class-based IPv4 In the future, more machines and networks will be implementing IPv6 subnetting | • Not futureproof • Compatibility issues with outside services or machines • Lower security benefits • Limited IP address whenever number of users increases | Support Centre Company | 0.8 | 80 | 64 | A) Ensure all machines used have IPv6 integration | In place | 0.5 | 60 | 30
[7 empty] | B) Ensure network devices have IPv6 integration | In place
[7 empty] | C) Ensure DNS is to date with the IPv6 changes | In place
[7 empty] | D) Hold a workshop in teaching employees on using IPv6 infrastructure | In place
4 | Physical layer cabling CAT 5e Only implementing CAT 5e may lead to inteferences during an urgent support calls | • Limited transfer speed • Lower security benefits • Affected by electromagnetic interferences (Inconsistent data transfer) • Limited range/length | Support Centre Company | 0.7 | 80 | 56 | A) Consult with a network adviser to plan physical layer before implementing | In place | 0.4 | 70 | 28
[7 empty] | B) Ensure that budget is within range to implement cabling changes | In place
[7 empty] | C) Train employees in the usage, handling and maintenance of the new cabling | In place
[7 empty] | Have constant maintenance on cabling to ensure its in good condition | Monthly
5 | Main Rounting Protocol is RIP v1 Does not have two factor authetication which leads to easier security breaches. Moreover due to its limited scope of data transfer, network congestion may occur | • Lacking in security measures • Lacks variable subnet masking • Less features than other options (Such as the lack of multicasting) • May have lower transfer speed | Support Centre Company | 0.9 | 90 | 81 | A) Consult with a network adviser to plan the machines/network devices needed for implementing RIP v2 | In place | 0.5 | 80 | 40
[7 empty] | B) Implement more security measures (Two factor authentication) with RIP v2 | In place
[7 empty] | Create a backup of data frequently in the case of data loss | Daily
[7 empty] | Have constant monitoring of the network to ensure it functions as intended | Daily
6 | Open source web server and anti-virus software are in use Due its open source nature, it may take more time and effort to implement updates/changes. Besides that, it may also be lead to easier security attacks due to its lack of security measures compared to a proprietary one | • Lower security benefits • Compatibility issues with different systems • Harder to maintain • May lack technical support | Support Centre Company | 0.7 | 90 | 63 | A) Consult with a network adviser and proprietary server provider to observe whether the current server is sufficient | In place | 0.3 | 80 | 24
[7 empty] | B) Ensure that budget is within range to implement a proprietary server | In place
[7 empty] | C) Hold a workshop to train employees in using the proprietary server implemented | In place
[7 empty] | D) Make sure anti- virus is compatible with proprietary server | In place
[7 empty] | Update anti-virus when a major update is needed | When available
[7 empty] | Have constant monitoring of the server to ensure it is running as expected, help for the proprietary server provider may also be requested | Daily
7 | Key network services uses a single 15 character password for authentication A single 15 character password is not enough of a security measure by itself as it is vulnerable to multiple types of security breaching such as password sniffing thus instantly accessing the network without other/more layers of security authentication | • Great secuity risk • Risk information getting leak | Support Centre Company | 0.9 | 90 | 81 | A) Ensure that another/more factors of authentication are implemented in conjunction with the 15 character password | In place | 0.5 | 90 | 45
[7 empty] | B) Encrypt the 15 character password | In place
[7 empty] | C) Have a safely stored document of the 15 character password as well the authentications used so that new hires in charge of the network services can obtain them securely. | In place
[7 empty] | Change the password/authentication whenever the person in charge of network services changes | When condition is met
8 | USB and external adaptors are allowed A security breaching virus/program may be intentinally/unintentionally brought to the workplace which could compromise the whole user base of the network being used | • Increased security risked • Risk information getting leak | Support Centre Company | 0.7 | 90 | 63 | A) Only allow authorised users to have access to server privileges | In place | 0.2 | 90 | 18
[7 empty] | B) Implement a network segmentation to split vital data from the general network | In place
[7 empty] | C) Only allow the use of company provided USB/adaptors which will then be returned at the end of work | In place
[7 empty] | D) Implement endpoint protection that detects the use of unauthorised USB/adaptors | In place